## Sheet2
Column1 | Known Defects TBF (To Be Fixed) | Column2 | Column3 | Column4 | Column5
1 | When you save a puzzle, it does not overwrite the old version of that puzzle but makes a new one instead | N/A | Uncomplete! | TBD | Will be fixed when we have a real database
2 | Disable Save Button after it's clicked until new changes made | N/A | Uncomplete! | TBD | TBF in I2
3 | Printing to Console when puzzle is solved | N/A | Complete! | 5 min | Created a popup when you click check solution
4 | Default Values Bug when you save a puzzle | N/A | Complete! | 10 min | Default blank values so you have to choose a category, difficulty, etc.
5 | Tabbing on Create Screen is weird | N/A | Uncomplete! | TBD | TBF in I2 (Maybe I3, Low Priority)
6 | Welcome screen addition | N/A | Complete! | 1 hours | A little welcome to our app message
7 | Encryption & Decryption Bugs | N/A | Complete! | 1 hours | Oopsie, didn't decrypt properly, changed Cryptogram class structure to better suit needs
8 | Shouldn't Be Able to Save A Blank Puzzle | N/A | Uncomplete! | T1 | TBF in I2

## Sheet3
# | Developer Task | Estimated Time | Complete? | Actual Time | Comments
1 | Edit Button | 2 hours | Complete | 1 hour | N/A
2 | Funcationality for Edit Button | 2 hours | Complete | 1.5 hours | N/A
3 | Delete Button | 2 hours | Complete | 1 hour | N/A
4 | Funcationality for Delete Button | 2 hours | Complete | 1.5 hours | N/A
5 | Embelish Solved/Not Solved Dialog Boxes | 1 hour | Complete | 1 hour | N/A
6 | Acceptance Tests | 8 hours | Complete | 10 hours | N/A
7 | Integration Tests | 5 hours | Complete | 4 hours | N/A
8 | Random Number Generator Stub | 2 hours | Complete | 2 hours | N/A
9
10