## Sheet2
Column1 | Known Defects TBF (To Be Fixed) | Column2 | Column3 | Column4 | Column5
1 | When you save a puzzle, it does not overwrite the old version of that puzzle but makes a new one instead | N/A | Uncomplete! | TBD | Will be fixed when we have a real database
2 | Disable Save Button after it's clicked until new changes made | N/A | Uncomplete! | TBD | TBF in I2
3 | Printing to Console when puzzle is solved | N/A | Complete! | 5 min | Created a popup when you click check solution
4 | Default Values Bug when you save a puzzle | N/A | Complete! | 10 min | Default blank values so you have to choose a category, difficulty, etc.
5 | Tabbing on Create Screen is weird | N/A | Uncomplete! | TBD | TBF in I2 (Maybe I3, Low Priority)
6 | Welcome screen addition | N/A | Complete! | 1 hours | A little welcome to our app message
7 | Encryption & Decryption Bugs | N/A | Complete! | 1 hours | Oopsie, didn't decrypt properly, changed Cryptogram class structure to better suit needs
8 | Shouldn't Be Able to Save A Blank Puzzle | N/A | Uncomplete! | T1 | TBF in I2

## Sheet3
# | Developer Task | Estimated Time | Complete? | Actual Time | Comments
1 | Add transition from solving to search screen | 2 hours | Complete | 1 hour | Can now select a puzzle from list and press "Play puzzle" and you will be taken to a solve screen
2 | Create User Class | 1 hour | Complete | 2 hours | Now can add a user and manipulate a user object
3 | Enumerate Categories and Difficulties | 1 hour | Complete | 1 hour | Categories and Difficulties are now enumerated classes instead of hard coded string
4 | Add Solve Screen | 2 hours | Complete | 1 hour | Solve screen hooked up to play button so you can now solve puzzle
5 | Solve GUI issues addressed in It 1 mark | 1 hour | Complete | 1 hour 30 min | N/A
6 | Scrolling in Cryptogram widget | 1 hour | Complete | 1 hour | Max text limit set for plaintext, scrolls if it is longer than the disply box
7 | Implement Find Screen Filters | 4 hours | Complete | 6 hours | Filtering puzzles on find screen now works
8 | Business Layer Login | 2 hours | Complete | 3 hours | Login In Logic Added
9 | Word Search | 4 days | Incomplete | N/A | Pushed to Iteration 3 (hopefully!)
10 | Play/Edit/Delete Buttons | 2 days | Incomplete | 2 hours | Play is there, edit and delete are pushed to iteration 3
11 | Connect users to puzzles | 1 day | Complete | 2 hours | N/A
12 | Login Screen GUI | 2 hours | Complete | 2 hours | N/A
13 | Sign up Screen GUI | 2 hours | Complete | 2 hours | N/A
14 | My puzzles button | 1 hour | Complete | 1 hour 30 min | My Puzzles button filters by user and takes you to find screen
15 | Database | 1 days | Complete | 7 hours 30 min | Database added! w00t
16
17
# | Known Defects TBF (To Be Fixed) | Open/Closed/In Progress | Time Taken | Comments
1 | Play Selected Puzzle Bug | Closed | 1 hour 30 min | Fixed
2 | Save Button Issue | Closed | 1 hour | Fixed
3 | Funny Tabbing | Open | N/A | Pushed to It 3
4 | Database Error (Missing Single Quotes on strings) | Closed | 15 min | Fixed
5 | General Refactoring and Bugs | In Progress | 13 hours | This is ongoing
6
7
8