## Sheet2
Column1 | Known Defects TBF (To Be Fixed) | Column2 | Column3 | Column4 | Column5
1 | When you save a puzzle, it does not overwrite the old version of that puzzle but makes a new one instead | N/A | Uncomplete! | TBD | Will be fixed when we have a real database
2 | Disable Save Button after it's clicked until new changes made | N/A | Uncomplete! | TBD | TBF in I2
3 | Printing to Console when puzzle is solved | N/A | Complete! | 5 min | Created a popup when you click check solution
4 | Default Values Bug when you save a puzzle | N/A | Complete! | 10 min | Default blank values so you have to choose a category, difficulty, etc.
5 | Tabbing on Create Screen is weird | N/A | Uncomplete! | TBD | TBF in I2 (Maybe I3, Low Priority)
6 | Welcome screen addition | N/A | Complete! | 1 hours | A little welcome to our app message
7 | Encryption & Decryption Bugs | N/A | Complete! | 1 hours | Oopsie, didn't decrypt properly, changed Cryptogram class structure to better suit needs
8 | Shouldn't Be Able to Save A Blank Puzzle | N/A | Uncomplete! | T1 | TBF in I2

## Sheet3
# | Developer Task | Estimated Time | Complete? | Actual Time | Comments
1 | Create Puzzle UI Design | 2 hours | Complete! | 2 hours 30 min | N/A
2 | Create Cryptogram Class & Testing | 3 hours | Complete! | 10 hours | N/A
3 | Find and Solve UI Design | 2 hours | Complete! | 2 hours | N/A
4 | Main Screen GUI | 4 hours | Complete! | 4 hours 45 min | N/A
5 | Search Screen GUI | 7 hours | Complete! | 4 hours | N/A
6 | Connecting Business Layer to Create/Search Screen | 2 hours | Complete! | 2 hours | N/A
7 | Transition Solve Screen from Search Screen | 4 hours | Uncomplete! | N/A | Pushed to I2, some kinks
8 | Create Test Suite | 3 hours | Complete! | 3 hours | N/A
9 | Create Parent Puzzle Class | 1 hour | Complete! | 30 min | N/A
10 | Create Screen GUI | 8 hours | Complete! | 7 hours | N/A
11 | Business Layer | 4 hours | Complete! | 3 hours | N/A
12 | Implement Save Button | 1 hour | Complete! | 1 hours | N/A
13 | Persistance Layer | 2 hours | Complete! | 1 hours | N/A
14 | 3 - Tier Diagram | 1 hour | Complete! | 30 min | N/A
15 | Write Readme for Iteration 1 | 1 hour | Complete! | 1 hours | N/A
16 | Check Solution Popup | 30 min | Complete! | 15 min | N/A
17 | Add Solve Screen | 2 hours | Uncomplete! | N/A | Pushed to I2, shouldn't take long
18 | Word Search Implementation | 15 hours | Uncomplete! | N/A | We didn't realize how long this would all take, Pushed to I2
19 | Crossword Implementation | 18 hours | Uncomplete! | N/A | See above comment, probably pushed to I3
# | Known Defects TBF (To Be Fixed) | Open/Closed/In Progress | Time Taken | Comments
1 | When you save a puzzle, it does not overwrite the old version of that puzzle but makes a new one instead | Open | TBD | Will be fixed when we have a real database
2 | Disable Save Button after it's clicked until new changes made | Open | TBD | TBF in I2
3 | Printing to Console when puzzle is solved | Closed | 5 min | Created a popup when you click check solution
4 | Default Values Bug when you save a puzzle | Closed | 10 min | Default blank values so you have to choose a category, difficulty, etc.
5 | Tabbing on Create Screen is weird | Open | TBD | TBF in I2 (Maybe I3, Low Priority)
6 | Welcome screen addition | Closed | 1 hours | A little welcome to our app message
7 | Encryption & Decryption Bugs | Closed | 1 hours | Oopsie, didn't decrypt properly, changed Cryptogram class structure to better suit needs
8 | Shouldn't Be Able to Save A Blank Puzzle | Open | T1 | TBF in I2